## Establishment
Home Stretch Service Establishment Action Planner
|  |  |  | SERVICE ESTABLISHMENT | [5 empty] | SERVICE OPERATIONAL
Tasks/Activities | Lead | Reference Documents/Resources | Completed Actions | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
PLANNING
Liaison with CoP around Service Establishment Timeline | Staff 1 |  | At risk
Liaison with CoP around Staff Training and Development | Staff 2 |  | Behind
Explore and finalise how internal Leaving Care program and team members will collaborate with Home Stretch, and smooth transition of any U18 | Staff 3 |  | Completed
Establish implementation support meetings with CoP & Dept | Staff 4 |  | On Track
Staff 5
GOVERNANCE
Community of Practice Membership
Finalise and executive partnership agreement with all 3 parties
Completed Registration Paperwork
Nominated Guiding Panel Representative
Identifed Other Working Group Representatives
Signed Membership Agreement
Organisation Governance
Delegation of Authority for Approval of Invest In Me funding by Home Stretch coordinator/Transition Coach
Communication and Alignment of Agency Leadership with Community of Practice Approach
Practice Governance
Finalise policies related to Home Stretch program. i.e Outreach safety, Responding to Risk [Suicide and Self Harm], Use of Credit Cards,
STAFF
Coordinator
Align Home Stretch WA JDF with Agency JDF
Create Job Advert
Align Home Stretch WA Interview Schedule with Agency Policy/Practice
Optional - Access Support from CoP for Panel Membership [YP or Manager]
Staying On Facilitator
Align Home Stretch WA JDF with Corporate JDF
Create Job Advert
Align Home Stretch WA Interview Schedule with Agency Policy/Practice
Optional - Access Support from CoP for Panel Membership [YP or Trial Staff]
Transition Coach
Align Home Stretch WA JDF with Corporate JDF
Create Job Advert
Align Home Stretch WA Interview Schedule with Agency Policy/Practice
Optional - Access Support from CoP for Panel Membership [YP or Trial Staff]
Transition Coach (50D) for ACCO
Align Home Stretch WA JDF with Corporate JDF
Create Job Advert
Align Home Stretch WA Interview Schedule with Agency Policy/Practice
Aboriginal Staff member available for Interview Panel
Admin Support
Create Job Advert
All Staff
Complete Agency Specific Induction and Core Training
Connect with CoP around planning for core training
EQUIPMENT/SYSTEMS
Outreach Vehicles
Mobile Phones
Laptops/Computer Access
Client Data/Records Management System
Home Stretch Minimum Data Set Captured
Access to Home Stretch WA Provider Website for Resources
OPERATIONAL PROCESSES
Invest In Me - Payment Mechanism for Coaches <100
Invest In Me - Payment Mechanism for Co-ordinators >$100
Recording and Auditing Mechanism for IIM Payments
Outreach Safety Policy
Serious Issue/Critical Incident Risk Management Policy and Practice for Staff
Intake and Referral Client Tracking Database [aligned with CoP Spreadsheet Template for data recording]
Explore and finalise how internal Leaving Care programs will collaborate with Home Stretch, and protocols for transitioning from waitlist.
Estalishment Meetings with CoP and District Offices Champions to establish Referral Pathways and protocols for communicating
Demand Management Approach Discussed during early establishment
SERVICE ACTIVITIES
Intake/Allocation Meeting
Case Discussion Meeting
Team Meetings
STAKEHOLDER ENGAGAGEMENT
Local District Engagement and Connection Workshops with Community of Practice
Plan for Co-location of Transition Coaches in District Offices
Support Circle Mapping - Program Level [Identify local relevant supports and community services across all domains of support]
Protocols with Leaving Care Service Provider around young people waitlist
MARKETING & PROMOTION
Explore use of Home Stretch WA Branding and Style Guide beyond forms
Integration/Alignment of Corporate Branding as needed
Communication Plan for local stakeholders about operationalising the service
YOUTH PARTICIPATION
Identified young people with lived experience for recruitment panels
Trained young people for recruitment panels [Privacy, Scope, Role, Boundaries]
Identified staff member to act as liaison for Home Stretch Youth Advisory Group

## DO NOT DELETE
Lead | Status
Staff 1 | At risk
Staff 2 | Behind
Staff 3 | Completed
Staff 4 | On Track
Staff 5